## Master
Commissioning Checklist for Unit Processes and Associated Building Systems
Instructions:
1. Copy Master Spreadsheet, Rename, save, and edit renamed file. DO NOT EDIT THE MASTER.
2. Customize form for a particular project by deleting or shading devices not part of project. (For example, if mixed liquor pumps do not exist, shade out that column of cells.)
3. Complete each blank with Yes, No or NR(not required)
4. If an item is not required by contract for a particular piece of equipment, shade out that particular cell. (For example, if a factory performance test is not required by contract for influent pumps, shade out the cell in that item row in the influent pump column.)
PUMPING SYSTEMS
Item No. | LARGE PUMPS - units with high level of documentation and potential witnessed factory test | Influent Pumps | Wet Weather Pumps | Mixed Liquor Pumps | Effluent Pumps | Large Pump 5 | Large Pump 6 | Large Pump 7
1 | Has final system head and pump system curves been received?
2 | Has certified performance test data been received?
3 | Has certified motor data been received?
4 | Has final approved shop drawings been received?
5 | Has final approved O&M manual been received?
6 | Has manufacturer inspected the installation?
7 | Has manufacturer O&M training occurred?
8 | Is pump covered by a new or existing on-line training module?
9 | Have manufacturer startup and functional tests occurred?
10 | Has functionality of manufacturer control system been demonstrated?
11 | Has vendor control panel/facility SCADA system interface been successfully demonstrated?
12 | Were factory performance tests witnessed?
13 | Were field performance tests witnessed?
14 | Has warranty been received?
15 | Have spare parts been received and turned over to Treatment Division?
Item No. | SMALL PUMPS WITH CONTROL PANELS - pumps of any size for which non-unit specific certification is acceptable and for which factory tests will not be witnessed | Grit Pumps | RAS/WAS Pumps | NARCY Recycle Pumps | Non-potable Water Pumps | Potable Water Pumps | Unthickened Sludge Pumps | Groundwater Pumps
1 | Has final system head and pump system curves been received?
2 | Has certified performance test data been received?
3 | Has representative motor data been received?
4 | Has final approved shop drawings been received?
5 | Has final approved O&M manual been received?
6 | Has manufacturer inspected the installation?
7 | Has manufacturer O&M training occurred?
8 | Is pump covered by a new or existing on-line training module?
9 | Have manufacturer startup and functional tests occurred?
10 | Has functionality of manufacturer control system been demonstrated?
11 | Has vendor control panel/facility SCADA system interface been successfully demonstrated?
12 | Were field performance tests witnessed?
13 | Has warranty been received?
14 | Have spare parts been received and turned over to Treatment Division?
Item No. | THICKENED SLLUDGE PUMPS - pumps of any size pumping slurries with sufficient solids that the solids affect the pumping characteristics and for which non-unit specific certification is acceptable and for which factory tests will not be witnessed | Thickened Primary Sludge Pumps | Thickened WAS Pumps | Dewatering Equipment Feed Pumps | Other Thickened Sludge Pump 1 | Other Thickened Sludge Pump 2 | Other Thickened Sludge Pump 3 | Other Thickened Sludge Pump 4
1 | Has final system head and pump system curves been received?
2 | Has certified performance test data been received?
3 | Has representative motor data been received?
4 | Has final approved shop drawings been received?
5 | Has final approved O&M manual been received?
6 | Has manufacturer inspected the installation?
7 | Has manufacturer O&M training occurred?
8 | Is pump covered by a new or existing on-line training module?
9 | Have manufacturer startup and functional tests occurred?
10 | Has functionality of manufacturer control system been demonstrated?
11 | Has vendor control panel/facility SCADA system interface been successfully demonstrated?
12 | Has field demonstration test been performed with thickened sludge?
13 | Were field performance tests witnessed?
14 | Has warranty been received?
15 | Have spare parts been received and turned over to Treatment Division?
Item No. | SMALL PUMPS WITHOUT CONTROL PANELS - smaller pumps without control panels for which minimal documentation is required | Sump Pump 1 | Sump Pump 2 | Sump Pump 3 | Other Small Pump 1 | Other Small Pump 2 | Other Small Pump 3 | Other Small Pump 3
1 | Has final system head and pump system curves been received?
2 | Has representative pump and motor performance test data been received?
3 | Has final approved shop drawings been received?
4 | Has final approved O&M manual been received?
5 | Has contractor provided startup and training?
6 | Have spare parts been received and turned over to Treatment Division?
7 | Were field performance tests witnessed?
8 | Has warranty been received?
PRELIMINARY TREATMENT PROCESS EQUIPMENT
Item No. | COMMINUTORS AND SCREENING EQUIPMENT | Comminutors | Influent Screens | Screenings Dewatering Equipment | Screenings conveyor | Other Screening Equipment 1 | Other Screening Equipment 2 | Other Screening Equipment 3
1 | Has representative equipment and motor performance test data been received?
2 | Has final approved shop drawings been received?
3 | Has final approved O&M manual been received?
4 | Has manufacturer inspected the installation?
5 | Has manufacturer startup occurred?
6 | Has manufacturer O&M training occurred?
7 | Is equipment covered by a new or existing on-line training module?
8 | Has functionality of manufacturer control system been demonstrated?
9 | Has vendor control panel/facility SCADA system interface been successfully demonstrated?
10 | Have spare parts been received and turned over to Treatment Division?
11 | Have electrical and control checks been completed (see separate checklist)
12 | Has warranty been received?
Item No. | GRIT REMOVAL AND PRIMARY TREATMENT | Grit In-tank Equipment | Grit Classifier | Grit Conveying | Primary Clarifier Collector | Scum Collection & Management | Other Equipment 1 | Other Equipment 2
1 | Has representative equipment and motor performance test data been received?
2 | Has final approved shop drawings been received?
3 | Has final approved O&M manual been received?
4 | Has manufacturer inspected the installation?
5 | Has manufacturer startup occurred?
6 | Has manufacturer O&M training occurred?
7 | Is equipment covered by a new or existing on-line training module?
8 | Have electrical and control checks been completed (see separate checklist)
9 | Has warranty been received?
10 | Have spare parts been received and turned over to Treatment Division?
SECONDARY TREATMENT PROCESS EQUIPMENT
Item No. | SECONDARY TREATMENT | Aeration Blowers | Diffuser System | Clarifier Collector Mechanism | Scum Collection Equipment | Other Equipment 1 | Other Equipment 2 | Other Equipment 3
1 | Has representative equipment performance test data been received?
2 | Has representative (certified if larger than 250 HP) motor performance test data been received?
3 | Has final approved shop drawings been received?
4 | Has final approved O&M manual been received?
5 | Has manufacturer inspected the installation?
6 | Has manufacturer startup and functional tests occurred?
7 | Has manufacturer O&M training occurred?
8 | Is equipment covered by a new or existing on-line training module?
9 | Have electrical and control checks been completed (see separate checklist)
10 | Has functionality of manufacturer control system been demonstrated?
11 | Has vendor control panel/facility SCADA system interface been successfully demonstrated?
12 | Has testing to demonstrate uniform air flow distribution been completed?
13 | Has warranty been received?
14 | Have spare parts been received and turned over to Treatment Division?
15 | Have clarifier torque tests been completed?
Item No. | DISINFECTION EQUIPMENT | UV Equipment System | HOCl Storage | HOCL Pump/meter Equipment | HOCL Injection Mixing Equipment | Dechlor Storage | Dechlor Pump/meter Equipment | Other Equipment 1
1 | Has representative equipment performance test data been received?
3 | Has final approved shop drawings been received?
4 | Has final approved O&M manual been received?
5a | Has UV manufacturer inspected the installation?
5b | Has contractor/vendor inspected the installation?
6a | Has UV manufacturer startup and functional tests occurred?
6b | Has contractor/vendor startup and functional tests occurred?
7a | Has UV manufacturer O&M training occurred?
7b | Has contractor/vendor O&M training occurred?
8 | Is equipment covered by a new or existing on-line training module?
9 | Have electrical and control checks been completed (see separate checklist)
10 | Has functionality of manufacturer control system been demonstrated?
11 | Has vendor control panel/facility SCADA system interface been successfully demonstrated?
12 | Is equipment covered by a new or existing on-line training module?
13 | Has warranty been received?
14 | Have spare parts been received and turned over to Treatment Division?
15 | Has UV level control failure to safe condition been demonstrated?
16 | Has chemical handling and storage safety equipment been demonstrated and accepted?
TERTIARY TREATMENT PROCESS EQUIPMENT
Item No. | FILTRATION | Underdrains and Troughs | Sweeps or Air Grids | Media | Air Wash Compressor | Disk Filters | Other Equipment 1 | Other Equipment 2
1 | Has representative equipment and motor performance test data been received?
2 | Has final approved shop drawings been received?
3 | Has final approved O&M manual been received?
4 | Has manufacturer inspected the installation?
5 | Has manufacturer startup occurred?
6 | Has manufacturer O&M training occurred?
7 | Is equipment covered by a new or existing on-line training module?
8 | Have spare parts been received and turned over to Treatment Division?
9 | Has functionality of manufacturer control system been demonstrated?
10 | Has vendor control panel/facility SCADA system interface been successfully demonstrated?
11 | Have electrical and control checks been completed (see separate checklist)
12 | Has warranty been received?
SOLIDS HANDLING EQUIPMENT
Item No. | SOLIDS THICKENING AND DIGESTION EQUIPMENT | Gravity Thickener Equipment | Gravity Belt Thickener | Dissolved Air Flotation Equipment | Thickening Centrifuge | Anaerobic Digestor | Other Equipment No. 1 | Other Equipment No. 2
1 | Has data from any required factory test been received?
2 | Has final approved shop drawings been received?
3 | Has final approved O&M manual been received?
4 | Has manufacturer inspected the installation?
5 | Has manufacturer O&M training occurred?
6 | Is equipment/system covered by a new or existing on-line training module?
7 | Have manufacturer startup and functional tests occurred?
8 | Were field performance tests witnessed?
9 | Has functionality of manufacturer control system been demonstrated?
10 | Has vendor control panel/facility SCADA system interface been successfully demonstrated?
11 | Has warranty been received?
12 | Have spare parts been received and turned over to Treatment Division?
Item No. | SLUDGE STORAGE AND ODOR CONTROL EQUIPMENT | Sludge Storage Aeration System | Sludge Storage Mixing Equipment | Sludge Storage Tank Covers or Domes | Ventilation Blowers | Odor Control Equipment | Odor control Chemical Feed System | Other Equipment No. 1
1 | Has data from any required factory test been received?
2 | Has final approved shop drawings been received?
3 | Has final approved O&M manual been received?
4 | Has manufacturer inspected the installation?
5 | Has manufacturer O&M training occurred?
6 | Is equipment/system covered by a new or existing on-line training module?
7 | Have manufacturer startup and functional tests occurred?
8 | Were field performance tests witnessed?
9 | Has functionality of manufacturer control system been demonstrated?
10 | Has vendor control panel/facility SCADA system interface been successfully demonstrated?
11 | Has warranty been received?
12 | Have spare parts been received and turned over to Treatment Division?
Item No. | SOLIDS DEWATERING EQUIPMENT | Belt filter Press | Dewatering Centrifure | Polymer Feed System | Coagulanet Feed System | Dewatered sludge Conveyors | Other Equipment No. 1 | Other Equipment No. 2
1 | Has data from any required factory test been received?
2 | Has final approved shop drawings been received?
3 | Has final approved O&M manual been received?
4 | Has manufacturer inspected the installation?
5 | Has manufacturer O&M training occurred?
6 | Is equipment/system covered by a new or existing on-line training module?
7 | Have manufacturer startup and functional tests occurred?
8 | Were field performance tests witnessed?
9 | Has functionality of manufacturer control system been demonstrated?
10 | Has vendor control panel/facility SCADA system interface been successfully demonstrated?
11 | Has warranty been received?
12 | Have spare parts been received and turned over to Treatment Division?
Item No. | SLUDGE DISPOSAL EQUIPMENT | Incinerator | Sludge Feed Conveyors | Ash Handling System | Sludge Loading or Receiving System | Incinerator Pollution Control Equipment | Other Equipment No. 1
1 | Has data from any required factory test been received?
2 | Has final approved shop drawings been received?
3 | Has final approved O&M manual been received?
4 | Has manufacturer inspected the installation?
5 | Has manufacturer O&M training occurred?
6 | Is equipment/system covered by a new or existing on-line training module?
7 | Have manufacturer startup and functional tests occurred?
8 | Were field performance tests witnessed?
9 | Has functionality of manufacturer control system been demonstrated?
10 | Has vendor control panel/facility SCADA system interface been successfully demonstrated?
11 | Has warranty been received?
12 | Have spare parts been received and turned over to Treatment Division?
ELECTRICAL AND I & C EQUIPMENT
Item No. | SWITCH GEARS, MCC's, AND VFD's | Switch Gear | MCC 1 | MCC2 | MCC 3 | VFD 1 | VFD 2 | VFD 3
1 | Has final approved shop drawings been received?
2 | Has final approved O&M manual been received?
3 | Were field performance tests occurred and witnessed?
4 | Has warranty been received?
Item No. | PLC's | PLC 1 | PLC 2 | PLC 3 | PLC 4 | PLC 5 | PLC 6 | PLC 7
1 | Has final approved shop drawings been received?
2 | Has final approved O&M manual been received?
3 | Were field performance tests occurred and witnessed?
4 | Has warranty been received?
5 | Have communication checks been completed and documented?
Item No. | LIGHTING AND POWER PANELS | LP/PP #___ | LP/PP #___ | LP/PP #___ | LP/PP #___ | LP/PP #___ | LP/PP #___ | LP/PP #___
1 | Has final approved shop drawings been received?
2 | Has final wiring diagram and load balance been received?
3 | Has warranty been received?
Item No. | POWER CONDUCTORS | Name______ | Name______ | Name______ | Name______ | Name______ | Name______ | Name______
1 | HaS resistance testing been completed and documents?
Item No. | OTHER ELECTRICAL EQUIPMENT | Name______ | Name______ | Name______ | Name______ | Name______ | Name______ | Name______
1 | Has final approved shop drawings been received?
2 | Has final approved O&M manual been received?
3 | Were field performance tests occurred and witnessed?
4 | Has warranty been received?
BUILDING MECHANICAL SYSTEMS
Item No. | AIR CONDITIONING UNITS | ACU #1 | ACU #2 | ACU #3 | ACU #4 | ACU #5 | ACU #6 | ACU #7
1 | Have final approved shop drawings been received?
2 | Has final approved O&M manual been received?
3 | Has manufacturer inspected the installation?
4 | Has manufacturer O&M training occurred?
5 | Is equipment/system covered by a new or existing on-line training module?
6 | Have manufacturer startup and functional tests occurred?
7 | Have Manufacturer inspection, testing, and startup reports been received?
8 | Has warranty been received?
9 | Have spare parts been received and turned over to Treatment Division?
10 | Has functionality of controls been demonstrated?
11 | Are filters installed and clean?
Item No. | HEATING UNITS | MAU # 1 | MAU # 2 | MAU # 3 | MAU # 4 | MAU # 5 | MAU # 6 | MAU # 7
1 | Has final approved shop drawings been received?
2 | Has final approved O&M manual been received?
3 | Has manufacturer inspected the installation?
4 | Has manufacturer O&M training occurred?
5 | Is equipment/system covered by a new or existing on-line training module?
6 | Have manufacturer startup and functional tests occurred?
7 | Have Manufacturer inspection, testing, and startup reports been received?
8 | Has warranty been received?
9 | Have spare parts been received and turned over to Treatment Division?
10 | Has functionality of controls been demonstrated?
Item No. | SUPPLY FANS | SF #1 | SF #2 | SF #3 | SF #4 | SF #5 | SF #6 | SF #7
1 | Has final approved shop drawings been received?
2 | Has final approved O&M manual been received?
3 | Has manufacturer inspected the installation?
4 | Has manufacturer O&M training occurred?
5 | Is equipment/system covered by a new or existing on-line training module?
6 | Have manufacturer startup and functional tests occurred?
7 | Have Manufacturer inspection, testing, and startup reports been received?
8 | Has warranty been received?
9 | Have spare parts been received and turned over to Treatment Division?
Item No. | EXHAUST FANS | EF #1 | EF #2 | EF #3 | EF #4 | EF #5 | EF #6 | EF #7
1 | Has final approved shop drawings been received?
2 | Has final approved O&M manual been received?
3 | Has manufacturer inspected the installation?
4 | Has manufacturer O&M training occurred?
5 | Is equipment/system covered by a new or existing on-line training module?
6 | Have manufacturer startup and functional tests occurred?
7 | Have Manufacturer inspection, testing, and startup reports been received?
8 | Has warranty been received?
9 | Have spare parts been received and turned over to Treatment Division?
BUILDINGS
Item No. | OCCUPIED BUILDINGS - Buildings with offices, restrooms, maintenance shop, break room, and/or other occupied space. | Building 1 | Building 2 | Building 3 | Building 4 | Building 5 | Building 6 | Building 7
1 | Has a Certificate of Substantial Completion, which establishes the Date of Substantial Completion, been executed?
2 | Has the Certificate of Occupancy been received?
3 | Have the final structural Special Inspection reports been received?
4 | If applicable, have final manifest and/or chain of custody records been received for the disposal of contaminated soils or hazardous materials?
5 | Has as constructed emergency exit signage and egress lighting been demonstrated and found acceptable?
6 | Has as constructed compliance with ADA standards been confirmed?
7 | Have all the Punch List items been completed?
8 | Has final air balance report been completed and received?
9 | Have final approved shop drawings and product data been received?
10 | Have final approved Operations and Maintenance manuals, including Emergency manuals been received?
11 | Have approved record drawings and record specifications been received from the contractor?
12 | Have completed record drawings been received in paper and electronic formats from the design professionals?
13 | Has demonstration of HVAC and other building systems and instruction of the staff in operation, adjustment, and maintenance of the systems occurred?
14 | Has the final report from the Building Commissioning agent been received?
15 | Have window, door and other warranties been received?
16 | Has a manufacturer's final roof inspection report been received?
17 | Has a listing of paint, flooring, and other finishes been received?
18 | Have tools, spare parts, extra materials and attic stock been received?
19 | Has the key control system been received by the owner?
20 | Are security systems and door access control systems operational?
Item No. | EQUIPMENT/PROCESS BUILDINGS - Normally unoccupied such as blower buildings, screen buildings, pump stations,…etc. | Building 1 | Building 2 | Building 3 | Building 4 | Building 5 | Building 6 | Building 7
1 | Has a Certificate of Substantial Completion, which establishes the Date of Substantial Completion, been executed?
2 | Has the Certificate of Occupancy been received?
3 | Have the final structural Special Inspection reports been received?
4 | If applicable, have final manifest and/or chain of custody records been received for the disposal of contaminated soils or hazardous materials?
5 | Has as constructed emergency exit signage and egress lighting been demonstrated and found acceptable?
6 | Has as constructed compliance with ADA standards been confirmed?
7 | Have all the Punch List items been completed?
8 | Has final air balance report been completed and received?
9 | Have final approved shop drawings and product data been received?
10 | Have final approved Operations and Maintenance manuals, including Emergency manuals been received?
11 | Have approved record drawings and record specifications been received from the contractor?
12 | Have completed record drawings been received in paper and electronic formats from the design professionals?
13 | Has demonstration of HVAC and other building systems and instruction of the staff in operation, adjustment, and maintenance of the systems occurred?
14 | Has the final report from the Building Commissioning agent been received?
15 | Have window, door and other warranties been received?
16 | Has a manufacturer's final roof inspection report been received?
17 | Has a listing of paint, flooring, and other finishes been received?
18 | Have tools, spare parts, extra materials and attic stock been received?
19 | Has the key control system been received by the owner?
20 | Are security systems and door access control systems operational?
LEED
Item No. | LEED CERTIFIED PROJECTS - Documentation for projects certified by Green Building Certification Institute (GBCI) and for owner certified buildings. | Building 1 | Building 2 | Building 3 | Building 4 | Building 5 | Building 6 | Building 7
1 | GBCI Certified projects
2 | Has the final report from the Building Commissioning agent been received?
3 | Has GBCI approved the project and awarded a certificate at the anticipated level?
4 | Has a GBCI certificate and plaque, if specified, been received?
5 | Has a copy of the complete credit documentation, including Project Profile been provided in both paper and electronic formats?
Owner Certified projects
6 | Has documentation for all Design credits been submitted by the design professionals and approved?
7 | Has documentation for all Construction credits been submitted by the contractor and approved?
8 | Has the final report from the Building Commissioning agent been received?
9 | Has the Owner certified the project at the anticipated level?
10 | Has a copy of the complete credit documentation, including Project Profile been provided in both paper and electronic formats?
CUSTOM CATEGORY
Item No. | (LIST CATEGORY HERE) | Item 1 | Item 2 | Item 3 | Item 4 | Item 5 | Item 6 | Item 7
|  |  | Item 2 |  | Item 4 | Item 5
1
2
3
4
5
6
7
8
9
10
11